## Sheet1
Date	Goal
18.11.2020	Create base github repository
25.11.2020	Create account management system and implement database
02.12.2020	Implement “Wellbeing” tab and connect it to database
09.12.2020	Implement “History of Wellbeing” tab and connect it to database
16.12.2020	Implement “Appointments” tab and connect it to database
23.12.2020	Implement “Medication” tab and connect it to database
06.01.2020	Implement Medical Staff additional functions
13.01.2020	Design with CSS, Optimize presentation of data (Test Design)
20.01.2020	Extra week